## Bug Report
Bug ID | Related TC | Resource | Endpoint | Title | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Impact | Evidence | Environment | Status
BUG-001 | TC-089 | Card | POST /cards | accepts request without required `name` field and returns 200 OK instead of rejecting it | 1. User has a valid API Key and a valid Token 2. An existing list is available | 1. Send POST request to https://api.trello.com/1/cards 2. Add query params: key={{key}}, token={{token}}, idList=<existing list id> 3. Do NOT include the name parameter 4. Send the request | Request should be rejected with 400 Bad Request since name is a required field for creating a card. | Request returns 200 OK and the card is created successfully despite name being omitted. | Medium | High | Allows creation of cards with missing/empty name, breaking API data validation contract. This can lead to unidentifiable cards in the UI, inconsistent data in the database, and unreliable behavior for any client or integration relying on name as a required field. | Screenshot attached (Postman response — Status: 200 OK, 425 ms) | Trello REST API (Production) – via Postman | Open
BUG-002 | TC-096 | Card | GET /cards/{id} | Get card with invalid "actions" query parameter value returns 200 OK instead of rejecting it | 1. User has a valid API Key and a valid Token 2. An existing card is available 3. actions parameter will be sent with an invalid value | 1. Use an existing valid card id 2. Send GET request to https://api.trello.com/1/cards/{cardId} 3. Add query params: key={{key}}, token={{token}}, actions=notARealAction 4. Send the request and check the Status Code | Request should be rejected with 400 Bad Request since "notARealAction" is not a supported value for the actions parameter (per Trello REST API documentation, actions accepts only true, false, or a valid comma-separated list of Action Types). | Request returns 200 OK (247 ms) and the card object is returned normally. The invalid actions value is silently ignored with no validation error and no actions data included in the response. | Low-Medium | Medium | Indicates missing input validation on the actions query parameter; invalid/misspelled filter values fail silently instead of alerting the API consumer, which can mask integration bugs on the client side. | Screenshot attached (Postman response — Status: 200 OK, 247 ms, 3.73 KB); Trello REST API documentation on actions_format nested resource parameters | Trello REST API (Production) – via Postman | Open